## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (High-Throughput Log Analytics & Monitoring Engine) | MUST HAVE | No Dependency | Kasthuri | 3- Completed
S1 | S1 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | Lucid Chart | Kasthuri | 3- Completed
S2 | S2 | US-001 | Document Discussion (Agile Template, Defect Tracker, Unit Testing) | MUST HAVE | No Dependency | Kasthuri | 3- Completed
S2 | S2 | US-001 | Use Case Research and Preparation | SHOULD HAVE | Project PDF | Kasthuri | 3- Completed
S3 | S3 | US-001 | Python practice Kit Completion (regex, parsing, logging) | MUST HAVE | HackerRank | Kasthuri | 3- Completed
S4 | S4 | US-001 | Dask/Ray practice Kit Completion | MUST HAVE | Official Docs | Kasthuri | 3- Completed
S5 | S5 | US-001 | Project Discussion Module 1 (Log Ingestion & Parsing Engine) | MUST HAVE | Python logging, regex | Kasthuri | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 2 (Distributed Processing Pipeline) | SHOULD HAVE | Dask/Ray | Kasthuri | 2- In Progress
S7 | S7 | US-001 | Project Discussion Module 3 (Anomaly Detection Core) | SHOULD HAVE | scikit-learn or PyOD | Kasthuri | 2- In Progress
S8 | S8 | US-001 | Project Discussion Module 4 (Alerting, Dashboard & Deployment) | MUST HAVE | SMTP, Slack, Streamlit/Dash | Kasthuri | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 23 | 12 | 10 | 9 | 7 | 7 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project (High-Throughput Log Analytics & Monitoring Engine) | 2026-02-09 | 2026-02-09 | Kasthuri | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Document | 2026-02-10 | 2026-02-11 | Kasthuri | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Document Discussion (Agile Template, Defect Tracker, Unit Testing) | 2026-02-11 | 2026-02-12 | Kasthuri | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Use Case Research and Preparation | 2026-02-13 | 2026-02-15 | Kasthuri | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | "Python practice Kit Completion (regex, parsing, logging)" | 2026-03-05 | 2026-03-08 | Sreeja, Kasthuri, Sheema, Ravi, Sai charan | Coding | 3- Completed | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Dask/Ray practice Kit Completion | 2026-02-24 | 2026-02-27 | Sreeja, Kasthuri, Sheema, Ravi, Sai charan | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Project Discussion Module 1 (Log Ingestion & Parsing Engine) | 12//02/2026 | 2026-02-20 | Kasthuri | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Project Discussion Module 2 (Distributed Processing Pipeline) | 2026-02-23 | 2026-03-03 | Kasthuri | Coding | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project Discussion Module 3 (Anomaly Detection Core) | 2026-03-04 | 2026-03-13 | Sreeja, Kasthuri, Sheema, Ravi, Sai charan | Integration Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | "Project Discussion Module 4 (Alerting, Dashboard & Deployment)" | 2026-03-16 | 2023-03-26 | Sreeja, Kasthuri, Sheema, Ravi, Sai charan | System Test | 2- In Progress | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on Dask/Ray cluster setup | Conducted a team brainstorming session and reviewed project PDF
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor
Sprint 2 | Day 7 | Difficulty in identifying all potential log sources | Conducted additional research on distributed log ingestion
Sprint 3 | Day 12 | Difficulty in debugging Python regex for log parsing | Collaborated with mentor to resolve issues
Sprint 4 | Day 16 | Dask/Ray jobs taking longer than expected | Optimized jobs with mentor support
Sprint 5 | Day 23 | Challenges integrating anomaly detection models | Scheduled team debugging session

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-11 | 2026-02-13 | Sreeja | Reviewing project PDF regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with mentor
2 | Sprint 2 | 2026-02-17 | 2026-02-20 | Sheema, Sai charan | Prioritizing Python practice for parsing | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | Sprint 3 | 2026-03-05 | 2026-03-06 | Kasthuri, Ravi | Preparing Dask/Ray practice | Rushing through concepts | Asking for help when stuck | Completed Dask/Ray practice with mentor support
4 | Sprint 4 | 2026-03-17 | 2026-03-20 | Sreeja, Kasthuri, Sheema, Ravi, Sai charan | Participating in Module 1 discussions | Delaying log ingestion exploration | Collaborating on parsing strategies | Completed Module 1 prototypes and received feedback